## Sheet1
	MSC CLASS Charter
Project Name :		MSC Class Website

Project Manager:		Kamlesh Kshirsagar				Project Sponsor		Satish Bhor

Status:		Approved

Start and End Date:		Start Date: 23/01/2025 End Date: 27/06/2025
		Start: Jan 24 End: Sept25
Project Description:		This project aims to design and develop a comprehensive and user-friendly website for a specific class. The website will serve as a centralized online platform for students and teachers, facilitating access to course materials, announcements, grades, and communication.

Project Team:		1. Aditya Kere					Backend Developer

		2. Nikhil Nagawade					UI/Ux designer

		3. Omkar Mule					Team Member

		4. Satish Bhor					Team Member

		5. Abhishek Magar					Tech Lead

Project scope:		Student login portal with access to: / Grades and assignments / Course materials (notes, presentations, readings) / Submission of assignments / Teacher login portal with access to: / Student grades and attendance / Upload and manage course materials / Create and post announcements / Communicate with students in

Constrains:		Time:		6 months
		Budget:		2 lakh
		Quality:		Prioritize time & budget

Benefits:		Ease of purchase for customers

		Easy Delivery

		Easy to payment

		The project encrypts all sensitive data and the purchase process is secure

Project Objective:		Develop a user-friendly and visually appealing website for a specific class. / Provide students and teachers with a centralized online platform for accessing course materials, announcements, grades, and communication. / Enhance student engagement and facilitate effective learning. / Improve communication and collaboration between students and teachers.

Key Stakeholders:		Project Manager
		Project Team
		Owner
		Students
Timeline And Key Milestone:		23 Jan : 31 Jan: Estimate the Website Cost
		2 Feb : 20 Feb Estimate time and resources
		20 Feb : 10 March Design the user interface
		10 March : 29 March building the database
		29 March : 3 may start building the website
		4 May : 20 May Test the website and measure performance
		3 June April launch the website
		27 june Closing
Risks:		Issues with coding, compatibility, or performance. / Difficulty in integrating different functionalities smoothly.

KAMLESH